## Cover
QUESTLY
Sprint & Milestone Plan
PROJECT | Questly
TEAM | 2 Developers (Dev 1 · Dev 2)
START DATE | March 3, 2026
DEADLINE | August 31, 2026
SPRINT LENGTH | 2 weeks per sprint
TOTAL SPRINTS | 13 sprints (S01 – S13)
MILESTONES | M1 – M8 (M1 complete)
TOTAL TASKS | 147 tasks across 13 sprints
SHEETS
→ Master Plan | Unified milestone + sprint + task hierarchy
→ Task Breakdown | 147 tasks with effort, layer, and owner
→ Testing Checkpoints | All test gates per milestone

## Master Plan
Questly — Master Plan
M1–M8 milestones with sprints and tasks ¦ Hierarchical layout ¦ M1 complete
ID | Name / Description | Start Date | End Date | Duration / Effort | Status / Layer | Assigned / Deps
M1 | Logic Plan & Database Schema | Mar 3, 2026 | Mar 3, 2026 | 2 wks | Complete | —
M2 | Project Structure Setup | Mar 3, 2026 | Mar 16, 2026 | 2 wks | In Progress | M1
S01 | Project Scaffolding | Mar 3, 2026 | Mar 16, 2026 | 2 weeks
T001 | Initialize Node.js + Express project with MVC folder structure |  |  | M | Backend | Dev 1
T002 | Set up PostgreSQL + Knex with connection pooling for dev/test/prod |  |  | M | Backend | Dev 1
T003 | Run all 10 DB migrations (workspaces, users, join_requests, sprints, tasks, task_assignments, rewards, reward_coupons, purchases, xp_transactions) |  |  | L | Backend | Dev 1
T004 | Configure .env, config module, and partial unique index on active sprints |  |  | S | Backend | Dev 1
T005 | Set up GitHub Actions CI/CD with backend, frontend, and E2E jobs (fail below 80% coverage) |  |  | M | DevOps | Dev 1
T006 | Initialize React 19 + Vite frontend project |  |  | S | Frontend | Dev 2
T007 | Configure Tailwind CSS v4 with Poppins font and design tokens |  |  | S | Frontend | Dev 2
T008 | Set up Zustand stores: authStore, taskStore, xpStore, sprintStore |  |  | M | Frontend | Dev 2
T009 | Configure React Router with all route definitions (/login, /dashboard, /tasks, /shop, /admin/*) |  |  | M | Frontend | Dev 2
T010 | Configure Vitest + React Testing Library with test factory helpers |  |  | S | DevOps | Dev 2
M3 | Auth & Workspace | Mar 17, 2026 | Apr 13, 2026 | 4 wks | Not Started | M2
S02 | Auth Backend + Basic Frontend | Mar 17, 2026 | Mar 30, 2026 | 2 weeks
T011 | POST /auth/register — create user with bcrypt-hashed password, return JWT |  |  | M | Backend | Dev 1
T012 | POST /auth/login — validate credentials against bcrypt hash, return signed JWT |  |  | M | Backend | Dev 1
T013 | POST /auth/logout — token invalidation (blacklist or stateless) |  |  | S | Backend | Dev 1
T014 | GET /auth/me — return current user info for valid Bearer token |  |  | S | Backend | Dev 1
T015 | verifyToken() middleware — validate JWT signature and expiry; return 401 if invalid |  |  | M | Backend | Dev 1
T016 | Role-based access control middleware — protect Admin-only routes; return 403 for Developers |  |  | M | Backend | Dev 1
T017 | POST /workspaces/ — Admin creates workspace with unique code and adminId |  |  | M | Backend | Dev 1
T018 | Sign-up screen with email, username, password fields and client-side validation |  |  | M | Frontend | Dev 2
T019 | Login screen with email/password form and wrong-credentials error display |  |  | M | Frontend | Dev 2
T020 | Auth Zustand store: user object, token, isAuthenticated, login/logout actions |  |  | M | Frontend | Dev 2
T021 | axios interceptor — attach Bearer token to all requests; handle 401 by triggering logout |  |  | M | Frontend | Dev 2
T022 | Protected route wrapper — redirect unauthenticated or wrong-role users |  |  | S | Frontend | Dev 2
S03 | Workspace, Join Flow & Auth Tests | Mar 31, 2026 | Apr 13, 2026 | 2 weeks
T023 | GET /workspaces/:id — return workspace details (Member access) |  |  | S | Backend | Dev 1
T024 | PATCH /workspaces/:id — Admin updates workspace name and settings |  |  | S | Backend | Dev 1
T025 | GET /workspaces/:id/members — Admin lists all approved workspace members |  |  | S | Backend | Dev 1
T026 | POST /workspaces/:id/join-requests — Developer submits a pending join request |  |  | M | Backend | Dev 1
T027 | GET /workspaces/:id/join-requests — Admin views all pending join requests |  |  | S | Backend | Dev 1
T028 | PATCH /workspaces/:id/join-requests/:id — Admin approves or rejects; if approved, assign workspace |  |  | M | Backend | Dev 1
T029 | Workspace creation screen (Admin) with shareable workspace code display |  |  | M | Frontend | Dev 2
T030 | Developer join request flow — enter workspace code, submit, show pending state |  |  | M | Frontend | Dev 2
T031 | Admin join-request review screen with approve/reject buttons and optimistic UI |  |  | M | Frontend | Dev 2
T032 | Role-based sidebar navigation (Developer: Tasks, Dashboard, Shop, Profile; Admin adds management screens) |  |  | M | Frontend | Dev 2
T033 | Unit tests: generateToken() returns valid JWT; verifyToken() decodes correctly; throws for expired/tampered |  |  | M | Testing | Dev 1
T034 | Integration tests: all auth endpoints (register, login, logout, /auth/me) |  |  | M | Testing | Dev 1
T035 | Integration tests: workspace endpoints and full join-request flow (submit → approve → access granted) |  |  | M | Testing | Dev 1
T036 | Security tests: Developer calls Admin-only endpoint → 403; unauthenticated → 401 |  |  | M | Testing | Shared
M4 | Jira Integration & Task Sync | Apr 14, 2026 | May 11, 2026 | 4 wks | Not Started | M3
S04 | Jira Connect + Task List UI | Apr 14, 2026 | Apr 27, 2026 | 2 weeks
T037 | POST /workspaces/:id/jira/connect — Admin stores Jira project key, access token, site URL |  |  | M | Backend | Dev 1
T038 | DELETE /workspaces/:id/jira/disconnect — Admin removes workspace-level Jira credentials |  |  | S | Backend | Dev 1
T039 | POST /users/me/jira/connect — Developer stores personal Jira access token and account ID |  |  | M | Backend | Dev 1
T040 | DELETE /users/me/jira/disconnect — Developer removes personal Jira credentials |  |  | S | Backend | Dev 1
T041 | Jira API client module — fetch all project issues via JQL with full pagination |  |  | L | Backend | Dev 1
T042 | POST /workspaces/:id/jira/sync — trigger full Jira sync and TaskAssignment reconciliation |  |  | L | Backend | Dev 1
T043 | Admin Jira connect screen — workspace-level: site URL, project key, access token, connect/disconnect |  |  | M | Frontend | Dev 2
T044 | Developer Jira connect screen — personal token input with connected/disconnected status indicator |  |  | M | Frontend | Dev 2
T045 | Task List screen layout — sprint header, FilterBar, scrollable task list, and empty state |  |  | M | Frontend | Dev 2
T046 | TaskCard component — title, difficulty badge (EASY/MEDIUM/HARD), status indicator, completion checkbox |  |  | M | Frontend | Dev 2
T047 | FilterBar component — All / Completed / High Priority tabs with difficulty dropdown |  |  | M | Frontend | Dev 2
S05 | Sync Logic, Task API & Jira Tests | Apr 28, 2026 | May 11, 2026 | 2 weeks
T048 | Task upsert logic — INSERT or UPDATE tasks using jira_issue_id as unique key (no duplicates on re-sync) |  |  | M | Backend | Dev 1
T049 | TaskAssignment reconciliation — add rows for newly assigned Jira users |  |  | L | Backend | Dev 1
T050 | TaskAssignment reconciliation — remove rows for unassigned users only if completedAt IS NULL |  |  | M | Backend | Dev 1
T051 | mapJiraIssueToDifficulty() — map Jira custom field to Easy/Medium/Hard; throw on unknown value |  |  | S | Backend | Dev 1
T052 | diffTaskAssignments() — return { toAdd, toRemove } sets by comparing Jira vs DB assignees |  |  | S | Backend | Dev 1
T053 | GET /workspaces/:id/tasks/ — task list with status, difficulty, and assignee query filters |  |  | M | Backend | Dev 1
T054 | GET /tasks/:id — single task with calling user's TaskAssignment completedAt status |  |  | S | Backend | Dev 1
T055 | Connect Task List to live GET /workspaces/:id/tasks/ API (replace stub data with live fetch) |  |  | M | Frontend | Dev 2
T056 | Implement FilterBar client-side filtering by status, difficulty, and priority |  |  | M | Frontend | Dev 2
T057 | Admin-only sync trigger button with loading spinner and 'Last synced X min ago' display |  |  | S | Frontend | Dev 2
T058 | Configure Nock to intercept all outgoing Jira HTTP calls at the network level in tests |  |  | M | Testing | Dev 1
T059 | Integration test — mocked Jira sync creates new tasks, updates existing, no duplicate tasks |  |  | M | Testing | Dev 1
T060 | Integration test — reconciliation adds new assignees and removes only unfinished TaskAssignments |  |  | M | Testing | Dev 1
T061 | Integration test — running sync twice with same data produces no duplicate tasks or TaskAssignments |  |  | M | Testing | Dev 1
T062 | Unit test — mapJiraIssueToDifficulty() maps all valid values; throws on unknown |  |  | S | Testing | Dev 1
T063 | Unit test — diffTaskAssignments() returns correct add/remove sets for all scenarios |  |  | S | Testing | Dev 1
M5 | XP System & Sprint Management | May 12, 2026 | Jun 8, 2026 | 4 wks | Not Started | M4
S06 | XP Engine + Sprint Lifecycle | May 12, 2026 | May 25, 2026 | 2 weeks
T064 | calculateXP(difficulty) — returns 20 (Easy), 40 (Medium), 70 (Hard); throws TypeError on unknown |  |  | S | Backend | Dev 1
T065 | POST /tasks/:id/complete — ACID chain: verify TaskAssignment, check completedAt, award XP, log transaction, set completedAt, update streak |  |  | L | Backend | Dev 1
T066 | POST /workspaces/:id/sprints/ — create sprint; return 409 if a sprint is already active |  |  | M | Backend | Dev 1
T067 | GET /workspaces/:id/sprints/ — list all workspace sprints sorted by startDate desc |  |  | S | Backend | Dev 1
T068 | GET /workspaces/:id/sprints/active — return current active sprint details |  |  | S | Backend | Dev 1
T069 | PATCH /sprints/:id — Admin updates sprint name and/or dates |  |  | S | Backend | Dev 1
T070 | POST /sprints/:id/close — ACID chain: set sprint completed, reset all members' sprint XP to 0, write sprint_reset transactions |  |  | L | Backend | Dev 1
T071 | Dashboard screen — XP progress bar section, active sprint card, high-priority tasks, streak counter |  |  | L | Frontend | Dev 2
T072 | XPProgressBar component — correct fill width, level label, and XP-to-next-level display |  |  | M | Frontend | Dev 2
T073 | useXP() hook — reads XP from Zustand xpStore; updates store after task completion |  |  | M | Frontend | Dev 2
T074 | Sprint status widget — shows sprint name, dates, days remaining, and active/completed badge |  |  | M | Frontend | Dev 2
S07 | Dashboard APIs, UI Completion & XP Tests | May 26, 2026 | Jun 8, 2026 | 2 weeks
T075 | GET /users/me/xp-history — return full XP transaction log with amount, reason, and timestamps |  |  | S | Backend | Dev 1
T076 | GET /users/me/dashboard — aggregated stats: XP, streak, level, active sprint, high-priority tasks |  |  | M | Backend | Dev 1
T077 | Streak calculation — increment if last activity was yesterday; reset to 1 if gap exceeds 1 day |  |  | M | Backend | Dev 1
T078 | Task completion interaction — checkbox → POST complete → '+40 XP' toast; update XP in store |  |  | M | Frontend | Dev 2
T079 | Level Up overlay — trigger on XP threshold crossing; show celebration modal with new level and Continue button |  |  | M | Frontend | Dev 2
T080 | Sprint management screen — Admin: create sprint form (name, dates) and Close Sprint button with confirmation |  |  | M | Frontend | Dev 2
T081 | XP history view — list past XP transactions with reason, amount (positive/negative), and date |  |  | S | Frontend | Dev 2
T082 | Unit test — calculateXP() returns 20/40/70 for Easy/Medium/Hard; throws TypeError on unknown |  |  | S | Testing | Dev 1
T083 | Integration test — task completion adds XP to both XP fields, writes xp_transaction, sets completedAt |  |  | M | Testing | Dev 1
T084 | Integration test — second completion on same TaskAssignment → 409; no duplicate XP awarded |  |  | M | Testing | Dev 1
T085 | Integration test — completing task with no TaskAssignment → 403 |  |  | S | Testing | Dev 1
T086 | Integration test — sprint close resets all members' sprint XP and writes sprint_reset transactions |  |  | M | Testing | Dev 1
T087 | Integration test — create sprint when one is already active → 409 |  |  | M | Testing | Dev 1
M6 | Reward Shop & Profile | Jun 9, 2026 | Jul 6, 2026 | 4 wks | Not Started | M5
S08 | Reward Shop Backend + UI | Jun 9, 2026 | Jun 22, 2026 | 2 weeks
T088 | POST /workspaces/:id/rewards/ — Admin creates reward (title, description, xpCost, imageUrl) |  |  | M | Backend | Dev 1
T089 | GET /workspaces/:id/rewards/ — Members browse available rewards with stock count |  |  | S | Backend | Dev 1
T090 | PATCH /rewards/:id — Admin updates reward details (title, description, xpCost, imageUrl) |  |  | S | Backend | Dev 1
T091 | DELETE /rewards/:id — Admin hard-deletes reward (only if no active coupons remain) |  |  | S | Backend | Dev 1
T092 | POST /rewards/:id/coupons/ — Admin adds coupon codes with expiresAt (default: 1 year) |  |  | M | Backend | Dev 1
T093 | isExpired(expiresAt) — returns true if past date; false if future; handles null safely |  |  | S | Backend | Dev 1
T094 | POST /rewards/:id/purchase/ — ACID chain: verify XP, lock valid coupon, deduct XP, create Purchase, log transaction, mark redeemed, update availability |  |  | L | Backend | Dev 1
T095 | Reward Shop screen — grid of reward cards with XP balance display and empty state |  |  | L | Frontend | Dev 2
T096 | RewardCard component — title, description, XP cost badge, availability, expired badge, Buy button |  |  | M | Frontend | Dev 2
T097 | Insufficient XP state — disable Buy button and show 'Not enough XP' tooltip |  |  | S | Frontend | Dev 2
T098 | Confirm purchase modal — reward name, XP cost, current balance, and XP remaining after purchase |  |  | M | Frontend | Dev 2
T099 | Admin reward management screen — add reward form and coupon codes upload textarea |  |  | M | Frontend | Dev 2
S09 | Profile, My Rewards & Shop Tests | Jun 23, 2026 | Jul 6, 2026 | 2 weeks
T100 | GET /users/me/purchases/ — My Rewards list (excludes soft-deleted, includes coupon expiry) |  |  | S | Backend | Dev 1
T101 | DELETE /users/me/purchases/:id — soft delete: set deletedAt; preserve row in DB for audit trail |  |  | M | Backend | Dev 1
T102 | GET /users/me/ — full profile: username, avatar, XP stats, streak, level, My Rewards list |  |  | M | Backend | Dev 1
T103 | PATCH /users/me/ — update username and/or avatarUrl |  |  | S | Backend | Dev 1
T104 | My Rewards / Profile screen — user stats section (XP, streak, level, avatar) with coupon list |  |  | L | Frontend | Dev 2
T105 | CouponCard component — reward name, masked coupon code (reveal on click), expiry date, delete button |  |  | M | Frontend | Dev 2
T106 | Expiry warning indicator — show warning badge on coupons with expiresAt within 30 days of today |  |  | M | Frontend | Dev 2
T107 | Soft delete coupon flow — delete button → confirmation dialog → optimistic removal from My Rewards |  |  | M | Frontend | Dev 2
T108 | Unit test — isExpired() returns true for past dates, false for future, handles null safely |  |  | S | Testing | Dev 1
T109 | Integration test — purchase flow: XP deducted, coupon redeemed, Purchase created, visible in My Rewards |  |  | M | Testing | Dev 1
T110 | Integration test — purchase with insufficient current_sprint_xp → 400 |  |  | S | Testing | Dev 1
T111 | Integration test — purchase when all coupons expired → 400; reward set to is_available=false |  |  | M | Testing | Dev 1
T112 | Integration test — soft delete: deletedAt set, row preserved, excluded from GET /users/me/purchases/ |  |  | M | Testing | Dev 1
T113 | Frontend test — RewardShop blocks buy when XP insufficient; shows expired badge when all coupons expired |  |  | M | Testing | Dev 2
T114 | Frontend test — MyRewards renders coupon list; delete triggers callback; expiry warning shown correctly |  |  | M | Testing | Dev 2
M7 | Frontend Integration | Jul 7, 2026 | Aug 3, 2026 | 4 wks | Not Started | M6
S10 | Frontend API Integration — Core Screens | Jul 7, 2026 | Jul 20, 2026 | 2 weeks
T115 | Axios API client — base URL from env, inject Bearer token, 401 interceptor → auto-logout |  |  | M | Frontend | Dev 2
T116 | Connect auth screens to live API (sign-up, login, JWT persistence, profile fetch on mount) |  |  | M | Frontend | Dev 2
T117 | Connect Task List, TaskCard, and FilterBar to live API with real task completion calls |  |  | M | Frontend | Dev 2
T118 | Connect Dashboard to live API — populate XP bar, sprint card, streak, and high-priority tasks |  |  | M | Frontend | Dev 2
T119 | Connect Reward Shop to live API (browse rewards and purchase with loading state) |  |  | M | Frontend | Dev 2
T120 | Global error handling — toast/banner for API errors (400, 403, 404, 500) and loading skeleton states |  |  | M | Frontend | Dev 2
S11 | Frontend Integration — Admin + E2E 1–2 | Jul 21, 2026 | Aug 3, 2026 | 2 weeks
T121 | Connect My Rewards / Profile to live API (GET profile, purchases, DELETE purchase, PATCH user) |  |  | M | Frontend | Dev 2
T122 | Connect Sprint management screen to live API (create, list, get active, close sprint) |  |  | M | Frontend | Dev 1
T123 | Connect Jira flows to live API — Admin workspace connect and Developer personal connect |  |  | M | Frontend | Dev 1
T124 | Admin workspace management screen — live member list and real join-request approval |  |  | M | Frontend | Dev 2
T125 | Token expiry handling — detect expired JWT, show re-login modal or auto-logout, clear auth state |  |  | M | Frontend | Dev 2
T126 | Frontend test — XPProgressBar renders correct fill width and level label for given XP values |  |  | S | Testing | Dev 2
T127 | Frontend test — TaskCard renders difficulty badge correctly; checkbox triggers completion callback |  |  | M | Testing | Dev 2
T128 | Frontend test — useXP() returns correct XP values and updates correctly after task completion |  |  | M | Testing | Dev 2
T129 | Frontend test — FilterBar applies correct logic for All / Completed / High Priority / difficulty combos |  |  | M | Testing | Dev 2
T130 | E2E Journey 1 — sign up, join workspace, connect Jira, sync tasks, complete task, verify XP on Dashboard |  |  | L | Testing | Shared
T131 | E2E Journey 2 — earn XP, purchase reward, verify coupon appears in My Rewards with correct expiry |  |  | L | Testing | Shared
M8 | E2E Testing & Write-up | Aug 4, 2026 | Aug 31, 2026 | 4 wks | Not Started | M7
S12 | E2E Journeys 3–5 + Security + Edge Cases | Aug 4, 2026 | Aug 17, 2026 | 2 weeks
T132 | E2E Journey 3 — purchase reward, confirm expiry warning shown, delete coupon, verify removal from My Rewards |  |  | M | Testing | Shared
T133 | E2E Journey 4 — Admin creates sprint, closes sprint, verify all developer XP bars reset to 0 |  |  | M | Testing | Shared
T134 | E2E Journey 5 — add Jira assignee → sync → TaskAssignment appears; remove → sync → TaskAssignment removed |  |  | L | Testing | Shared
T135 | Security tests — cross-workspace 403, Admin-only 403, wrong-workspace task completion 403 |  |  | M | Testing | Dev 1
T136 | Security tests — unauthenticated 401, Developer closes sprint 403, tampered JWT 401, SQL injection safe |  |  | M | Testing | Dev 1
T137 | Edge case tests (all 7): insufficient XP, expired coupons, double completion, no TaskAssignment, duplicate sprint, expired coupon, completed assignment preservation |  |  | L | Testing | Shared
T138 | Performance test — Jira sync with 100+ tasks and 10+ assignees/task completes within 3 seconds |  |  | M | Testing | Dev 1
S13 | Coverage, Write-up & Submission | Aug 18, 2026 | Aug 31, 2026 | 2 weeks
T139 | 10 developers complete different tasks simultaneously — no XP errors, no lost transactions (ACID guarantee) |  |  | M | Testing | Dev 1
T140 | 5 developers purchase last coupon simultaneously — exactly one succeeds, others receive 400 |  |  | M | Testing | Dev 1
T141 | Full coverage report — achieve ≥80% overall and 100% branch on critical modules; CI/CD gate passes |  |  | L | Testing | Shared
T142 | Update ER diagram (questly-schema.mermaid) to reflect final schema with task_assignments table |  |  | M | Documentation | Dev 1
T143 | Write API documentation — all endpoints: method, path, access level, request/response schema, error codes |  |  | M | Documentation | Shared
T144 | Write final project write-up — architecture, design decisions, testing strategy, lessons learned |  |  | L | Documentation | Shared
T145 | Prepare demo walkthrough for all 5 E2E journeys with talking points |  |  | M | Documentation | Shared
T146 | Final CI/CD run — all GitHub Actions checks green; upload final coverage report artifact |  |  | S | DevOps | Shared
T147 | Project submission — package all deliverables (repo, write-up, ER diagram, API docs, demo recording) |  |  | S | Documentation | Shared

## Task Breakdown
Questly — Task Breakdown
147 tasks across 13 sprints ¦ Effort: S ≈ 0.5 day · M ≈ 1 day · L ≈ 2–3 days
Task ID | Sprint | Milestone | Layer | Task Description | Effort | Assigned To | Duration | Dependency | Status
T001 | S01 | M2 | Backend | Initialize Node.js + Express project with MVC folder structure | M | Dev 1 | 1 day | — | Done | Done
T002 | S01 | M2 | Backend | Set up PostgreSQL + Knex with connection pooling for dev/test/prod | M | Dev 1 | 1 day | T001 | Done
T003 | S01 | M2 | Backend | Run all 10 DB migrations (workspaces, users, join_requests, sprints, tasks, task_assignments, rewards, reward_coupons, purchases, xp_transactions) | L | Dev 1 | 2.5 days | T002 | Done
T004 | S01 | M2 | Backend | Configure .env, config module, and partial unique index on active sprints | S | Dev 1 | 0.5 day | T001 | Done
T005 | S01 | M2 | DevOps | Set up GitHub Actions CI/CD with backend, frontend, and E2E jobs (fail below 80% coverage) | M | Dev 1 | 1 day | T001 | Done
T006 | S01 | M2 | Frontend | Initialize React 19 + Vite frontend project | S | Dev 2 | 0.5 day | — | Done
T007 | S01 | M2 | Frontend | Configure Tailwind CSS v4 with Poppins font and design tokens | S | Dev 2 | 0.5 day | T006 | Done
T008 | S01 | M2 | Frontend | Set up Zustand stores: authStore, taskStore, xpStore, sprintStore | M | Dev 2 | 1 day | T006 | Done
T009 | S01 | M2 | Frontend | Configure React Router with all route definitions (/login, /dashboard, /tasks, /shop, /admin/*) | M | Dev 2 | 1 day | T006 | Done
T010 | S01 | M2 | DevOps | Configure Vitest + React Testing Library with test factory helpers | S | Dev 2 | 0.5 day | T006 | Done
T011 | S02 | M3 | Backend | POST /auth/register — create user with bcrypt-hashed password, return JWT | M | Dev 1 | 1 day | T004
T012 | S02 | M3 | Backend | POST /auth/login — validate credentials against bcrypt hash, return signed JWT | M | Dev 1 | 1 day | T011
T013 | S02 | M3 | Backend | POST /auth/logout — token invalidation (blacklist or stateless) | S | Dev 1 | 0.5 day | T012
T014 | S02 | M3 | Backend | GET /auth/me — return current user info for valid Bearer token | S | Dev 1 | 0.5 day | T011
T015 | S02 | M3 | Backend | verifyToken() middleware — validate JWT signature and expiry; return 401 if invalid | M | Dev 1 | 1 day | T011
T016 | S02 | M3 | Backend | Role-based access control middleware — protect Admin-only routes; return 403 for Developers | M | Dev 1 | 1 day | T015
T017 | S02 | M3 | Backend | POST /workspaces/ — Admin creates workspace with unique code and adminId | M | Dev 1 | 1 day | T016
T018 | S02 | M3 | Frontend | Sign-up screen with email, username, password fields and client-side validation | M | Dev 2 | 1 day | T009
T019 | S02 | M3 | Frontend | Login screen with email/password form and wrong-credentials error display | M | Dev 2 | 1 day | T018
T020 | S02 | M3 | Frontend | Auth Zustand store: user object, token, isAuthenticated, login/logout actions | M | Dev 2 | 1 day | T018
T021 | S02 | M3 | Frontend | axios interceptor — attach Bearer token to all requests; handle 401 by triggering logout | M | Dev 2 | 1 day | T020
T022 | S02 | M3 | Frontend | Protected route wrapper — redirect unauthenticated or wrong-role users | S | Dev 2 | 0.5 day | T021
T023 | S03 | M3 | Backend | GET /workspaces/:id — return workspace details (Member access) | S | Dev 1 | 0.5 day | T017
T024 | S03 | M3 | Backend | PATCH /workspaces/:id — Admin updates workspace name and settings | S | Dev 1 | 0.5 day | T023
T025 | S03 | M3 | Backend | GET /workspaces/:id/members — Admin lists all approved workspace members | S | Dev 1 | 0.5 day | T023
T026 | S03 | M3 | Backend | POST /workspaces/:id/join-requests — Developer submits a pending join request | M | Dev 1 | 1 day | T017
T027 | S03 | M3 | Backend | GET /workspaces/:id/join-requests — Admin views all pending join requests | S | Dev 1 | 0.5 day | T026
T028 | S03 | M3 | Backend | PATCH /workspaces/:id/join-requests/:id — Admin approves or rejects; if approved, assign workspace | M | Dev 1 | 1 day | T027
T029 | S03 | M3 | Frontend | Workspace creation screen (Admin) with shareable workspace code display | M | Dev 2 | 1 day | T022
T030 | S03 | M3 | Frontend | Developer join request flow — enter workspace code, submit, show pending state | M | Dev 2 | 1 day | T029
T031 | S03 | M3 | Frontend | Admin join-request review screen with approve/reject buttons and optimistic UI | M | Dev 2 | 1 day | T030
T032 | S03 | M3 | Frontend | Role-based sidebar navigation (Developer: Tasks, Dashboard, Shop, Profile; Admin adds management screens) | M | Dev 2 | 1 day | T022
T033 | S03 | M3 | Testing | Unit tests: generateToken() returns valid JWT; verifyToken() decodes correctly; throws for expired/tampered | M | Dev 1 | 1 day | T022
T034 | S03 | M3 | Testing | Integration tests: all auth endpoints (register, login, logout, /auth/me) | M | Dev 1 | 1 day | T033
T035 | S03 | M3 | Testing | Integration tests: workspace endpoints and full join-request flow (submit → approve → access granted) | M | Dev 1 | 1 day | T034
T036 | S03 | M3 | Testing | Security tests: Developer calls Admin-only endpoint → 403; unauthenticated → 401 | M | Shared | 1 day | T035
T037 | S04 | M4 | Backend | POST /workspaces/:id/jira/connect — Admin stores Jira project key, access token, site URL | M | Dev 1 | 1 day | T028
T038 | S04 | M4 | Backend | DELETE /workspaces/:id/jira/disconnect — Admin removes workspace-level Jira credentials | S | Dev 1 | 0.5 day | T037
T039 | S04 | M4 | Backend | POST /users/me/jira/connect — Developer stores personal Jira access token and account ID | M | Dev 1 | 1 day | T037
T040 | S04 | M4 | Backend | DELETE /users/me/jira/disconnect — Developer removes personal Jira credentials | S | Dev 1 | 0.5 day | T039
T041 | S04 | M4 | Backend | Jira API client module — fetch all project issues via JQL with full pagination | L | Dev 1 | 2.5 days | T039
T042 | S04 | M4 | Backend | POST /workspaces/:id/jira/sync — trigger full Jira sync and TaskAssignment reconciliation | L | Dev 1 | 2.5 days | T041
T043 | S04 | M4 | Frontend | Admin Jira connect screen — workspace-level: site URL, project key, access token, connect/disconnect | M | Dev 2 | 1 day | T032
T044 | S04 | M4 | Frontend | Developer Jira connect screen — personal token input with connected/disconnected status indicator | M | Dev 2 | 1 day | T043
T045 | S04 | M4 | Frontend | Task List screen layout — sprint header, FilterBar, scrollable task list, and empty state | M | Dev 2 | 1 day | T032
T046 | S04 | M4 | Frontend | TaskCard component — title, difficulty badge (EASY/MEDIUM/HARD), status indicator, completion checkbox | M | Dev 2 | 1 day | T045
T047 | S04 | M4 | Frontend | FilterBar component — All / Completed / High Priority tabs with difficulty dropdown | M | Dev 2 | 1 day | T046
T048 | S05 | M4 | Backend | Task upsert logic — INSERT or UPDATE tasks using jira_issue_id as unique key (no duplicates on re-sync) | M | Dev 1 | 1 day | T042
T049 | S05 | M4 | Backend | TaskAssignment reconciliation — add rows for newly assigned Jira users | L | Dev 1 | 2.5 days | T048
T050 | S05 | M4 | Backend | TaskAssignment reconciliation — remove rows for unassigned users only if completedAt IS NULL | M | Dev 1 | 1 day | T049
T051 | S05 | M4 | Backend | mapJiraIssueToDifficulty() — map Jira custom field to Easy/Medium/Hard; throw on unknown value | S | Dev 1 | 0.5 day | T041
T052 | S05 | M4 | Backend | diffTaskAssignments() — return { toAdd, toRemove } sets by comparing Jira vs DB assignees | S | Dev 1 | 0.5 day | T051
T053 | S05 | M4 | Backend | GET /workspaces/:id/tasks/ — task list with status, difficulty, and assignee query filters | M | Dev 1 | 1 day | T050
T054 | S05 | M4 | Backend | GET /tasks/:id — single task with calling user's TaskAssignment completedAt status | S | Dev 1 | 0.5 day | T053
T055 | S05 | M4 | Frontend | Connect Task List to live GET /workspaces/:id/tasks/ API (replace stub data with live fetch) | M | Dev 2 | 1 day | T047
T056 | S05 | M4 | Frontend | Implement FilterBar client-side filtering by status, difficulty, and priority | M | Dev 2 | 1 day | T055
T057 | S05 | M4 | Frontend | Admin-only sync trigger button with loading spinner and 'Last synced X min ago' display | S | Dev 2 | 0.5 day | T056
T058 | S05 | M4 | Testing | Configure Nock to intercept all outgoing Jira HTTP calls at the network level in tests | M | Dev 1 | 1 day | T042
T059 | S05 | M4 | Testing | Integration test — mocked Jira sync creates new tasks, updates existing, no duplicate tasks | M | Dev 1 | 1 day | T058
T060 | S05 | M4 | Testing | Integration test — reconciliation adds new assignees and removes only unfinished TaskAssignments | M | Dev 1 | 1 day | T059
T061 | S05 | M4 | Testing | Integration test — running sync twice with same data produces no duplicate tasks or TaskAssignments | M | Dev 1 | 1 day | T060
T062 | S05 | M4 | Testing | Unit test — mapJiraIssueToDifficulty() maps all valid values; throws on unknown | S | Dev 1 | 0.5 day | T051
T063 | S05 | M4 | Testing | Unit test — diffTaskAssignments() returns correct add/remove sets for all scenarios | S | Dev 1 | 0.5 day | T052
T064 | S06 | M5 | Backend | calculateXP(difficulty) — returns 20 (Easy), 40 (Medium), 70 (Hard); throws TypeError on unknown | S | Dev 1 | 0.5 day | T054
T065 | S06 | M5 | Backend | POST /tasks/:id/complete — ACID chain: verify TaskAssignment, check completedAt, award XP, log transaction, set completedAt, update streak | L | Dev 1 | 2.5 days | T064
T066 | S06 | M5 | Backend | POST /workspaces/:id/sprints/ — create sprint; return 409 if a sprint is already active | M | Dev 1 | 1 day | T065
T067 | S06 | M5 | Backend | GET /workspaces/:id/sprints/ — list all workspace sprints sorted by startDate desc | S | Dev 1 | 0.5 day | T066
T068 | S06 | M5 | Backend | GET /workspaces/:id/sprints/active — return current active sprint details | S | Dev 1 | 0.5 day | T067
T069 | S06 | M5 | Backend | PATCH /sprints/:id — Admin updates sprint name and/or dates | S | Dev 1 | 0.5 day | T068
T070 | S06 | M5 | Backend | POST /sprints/:id/close — ACID chain: set sprint completed, reset all members' sprint XP to 0, write sprint_reset transactions | L | Dev 1 | 2.5 days | T069
T071 | S06 | M5 | Frontend | Dashboard screen — XP progress bar section, active sprint card, high-priority tasks, streak counter | L | Dev 2 | 2.5 days | T068
T072 | S06 | M5 | Frontend | XPProgressBar component — correct fill width, level label, and XP-to-next-level display | M | Dev 2 | 1 day | T071
T073 | S06 | M5 | Frontend | useXP() hook — reads XP from Zustand xpStore; updates store after task completion | M | Dev 2 | 1 day | T072
T074 | S06 | M5 | Frontend | Sprint status widget — shows sprint name, dates, days remaining, and active/completed badge | M | Dev 2 | 1 day | T073
T075 | S07 | M5 | Backend | GET /users/me/xp-history — return full XP transaction log with amount, reason, and timestamps | S | Dev 1 | 0.5 day | T070
T076 | S07 | M5 | Backend | GET /users/me/dashboard — aggregated stats: XP, streak, level, active sprint, high-priority tasks | M | Dev 1 | 1 day | T075
T077 | S07 | M5 | Backend | Streak calculation — increment if last activity was yesterday; reset to 1 if gap exceeds 1 day | M | Dev 1 | 1 day | T065
T078 | S07 | M5 | Frontend | Task completion interaction — checkbox → POST complete → '+40 XP' toast; update XP in store | M | Dev 2 | 1 day | T074
T079 | S07 | M5 | Frontend | Level Up overlay — trigger on XP threshold crossing; show celebration modal with new level and Continue button | M | Dev 2 | 1 day | T078
T080 | S07 | M5 | Frontend | Sprint management screen — Admin: create sprint form (name, dates) and Close Sprint button with confirmation | M | Dev 2 | 1 day | T079
T081 | S07 | M5 | Frontend | XP history view — list past XP transactions with reason, amount (positive/negative), and date | S | Dev 2 | 0.5 day | T080
T082 | S07 | M5 | Testing | Unit test — calculateXP() returns 20/40/70 for Easy/Medium/Hard; throws TypeError on unknown | S | Dev 1 | 0.5 day | T064
T083 | S07 | M5 | Testing | Integration test — task completion adds XP to both XP fields, writes xp_transaction, sets completedAt | M | Dev 1 | 1 day | T065
T084 | S07 | M5 | Testing | Integration test — second completion on same TaskAssignment → 409; no duplicate XP awarded | M | Dev 1 | 1 day | T083
T085 | S07 | M5 | Testing | Integration test — completing task with no TaskAssignment → 403 | S | Dev 1 | 0.5 day | T084
T086 | S07 | M5 | Testing | Integration test — sprint close resets all members' sprint XP and writes sprint_reset transactions | M | Dev 1 | 1 day | T070
T087 | S07 | M5 | Testing | Integration test — create sprint when one is already active → 409 | M | Dev 1 | 1 day | T066
T088 | S08 | M6 | Backend | POST /workspaces/:id/rewards/ — Admin creates reward (title, description, xpCost, imageUrl) | M | Dev 1 | 1 day | T081
T089 | S08 | M6 | Backend | GET /workspaces/:id/rewards/ — Members browse available rewards with stock count | S | Dev 1 | 0.5 day | T088
T090 | S08 | M6 | Backend | PATCH /rewards/:id — Admin updates reward details (title, description, xpCost, imageUrl) | S | Dev 1 | 0.5 day | T089
T091 | S08 | M6 | Backend | DELETE /rewards/:id — Admin hard-deletes reward (only if no active coupons remain) | S | Dev 1 | 0.5 day | T090
T092 | S08 | M6 | Backend | POST /rewards/:id/coupons/ — Admin adds coupon codes with expiresAt (default: 1 year) | M | Dev 1 | 1 day | T088
T093 | S08 | M6 | Backend | isExpired(expiresAt) — returns true if past date; false if future; handles null safely | S | Dev 1 | 0.5 day | T092
T094 | S08 | M6 | Backend | POST /rewards/:id/purchase/ — ACID chain: verify XP, lock valid coupon, deduct XP, create Purchase, log transaction, mark redeemed, update availability | L | Dev 1 | 2.5 days | T093
T095 | S08 | M6 | Frontend | Reward Shop screen — grid of reward cards with XP balance display and empty state | L | Dev 2 | 2.5 days | T081
T096 | S08 | M6 | Frontend | RewardCard component — title, description, XP cost badge, availability, expired badge, Buy button | M | Dev 2 | 1 day | T095
T097 | S08 | M6 | Frontend | Insufficient XP state — disable Buy button and show 'Not enough XP' tooltip | S | Dev 2 | 0.5 day | T096
T098 | S08 | M6 | Frontend | Confirm purchase modal — reward name, XP cost, current balance, and XP remaining after purchase | M | Dev 2 | 1 day | T097
T099 | S08 | M6 | Frontend | Admin reward management screen — add reward form and coupon codes upload textarea | M | Dev 2 | 1 day | T098
T100 | S09 | M6 | Backend | GET /users/me/purchases/ — My Rewards list (excludes soft-deleted, includes coupon expiry) | S | Dev 1 | 0.5 day | T094
T101 | S09 | M6 | Backend | DELETE /users/me/purchases/:id — soft delete: set deletedAt; preserve row in DB for audit trail | M | Dev 1 | 1 day | T100
T102 | S09 | M6 | Backend | GET /users/me/ — full profile: username, avatar, XP stats, streak, level, My Rewards list | M | Dev 1 | 1 day | T101
T103 | S09 | M6 | Backend | PATCH /users/me/ — update username and/or avatarUrl | S | Dev 1 | 0.5 day | T102
T104 | S09 | M6 | Frontend | My Rewards / Profile screen — user stats section (XP, streak, level, avatar) with coupon list | L | Dev 2 | 2.5 days | T099
T105 | S09 | M6 | Frontend | CouponCard component — reward name, masked coupon code (reveal on click), expiry date, delete button | M | Dev 2 | 1 day | T104
T106 | S09 | M6 | Frontend | Expiry warning indicator — show warning badge on coupons with expiresAt within 30 days of today | M | Dev 2 | 1 day | T105
T107 | S09 | M6 | Frontend | Soft delete coupon flow — delete button → confirmation dialog → optimistic removal from My Rewards | M | Dev 2 | 1 day | T106
T108 | S09 | M6 | Testing | Unit test — isExpired() returns true for past dates, false for future, handles null safely | S | Dev 1 | 0.5 day | T093
T109 | S09 | M6 | Testing | Integration test — purchase flow: XP deducted, coupon redeemed, Purchase created, visible in My Rewards | M | Dev 1 | 1 day | T094
T110 | S09 | M6 | Testing | Integration test — purchase with insufficient current_sprint_xp → 400 | S | Dev 1 | 0.5 day | T109
T111 | S09 | M6 | Testing | Integration test — purchase when all coupons expired → 400; reward set to is_available=false | M | Dev 1 | 1 day | T110
T112 | S09 | M6 | Testing | Integration test — soft delete: deletedAt set, row preserved, excluded from GET /users/me/purchases/ | M | Dev 1 | 1 day | T101
T113 | S09 | M6 | Testing | Frontend test — RewardShop blocks buy when XP insufficient; shows expired badge when all coupons expired | M | Dev 2 | 1 day | T097
T114 | S09 | M6 | Testing | Frontend test — MyRewards renders coupon list; delete triggers callback; expiry warning shown correctly | M | Dev 2 | 1 day | T106
T115 | S10 | M7 | Frontend | Axios API client — base URL from env, inject Bearer token, 401 interceptor → auto-logout | M | Dev 2 | 1 day | T021
T116 | S10 | M7 | Frontend | Connect auth screens to live API (sign-up, login, JWT persistence, profile fetch on mount) | M | Dev 2 | 1 day | T115
T117 | S10 | M7 | Frontend | Connect Task List, TaskCard, and FilterBar to live API with real task completion calls | M | Dev 2 | 1 day | T116
T118 | S10 | M7 | Frontend | Connect Dashboard to live API — populate XP bar, sprint card, streak, and high-priority tasks | M | Dev 2 | 1 day | T117
T119 | S10 | M7 | Frontend | Connect Reward Shop to live API (browse rewards and purchase with loading state) | M | Dev 2 | 1 day | T118
T120 | S10 | M7 | Frontend | Global error handling — toast/banner for API errors (400, 403, 404, 500) and loading skeleton states | M | Dev 2 | 1 day | T119
T121 | S11 | M7 | Frontend | Connect My Rewards / Profile to live API (GET profile, purchases, DELETE purchase, PATCH user) | M | Dev 2 | 1 day | T120
T122 | S11 | M7 | Frontend | Connect Sprint management screen to live API (create, list, get active, close sprint) | M | Dev 1 | 1 day | T121
T123 | S11 | M7 | Frontend | Connect Jira flows to live API — Admin workspace connect and Developer personal connect | M | Dev 1 | 1 day | T122
T124 | S11 | M7 | Frontend | Admin workspace management screen — live member list and real join-request approval | M | Dev 2 | 1 day | T123
T125 | S11 | M7 | Frontend | Token expiry handling — detect expired JWT, show re-login modal or auto-logout, clear auth state | M | Dev 2 | 1 day | T124
T126 | S11 | M7 | Testing | Frontend test — XPProgressBar renders correct fill width and level label for given XP values | S | Dev 2 | 0.5 day | T072
T127 | S11 | M7 | Testing | Frontend test — TaskCard renders difficulty badge correctly; checkbox triggers completion callback | M | Dev 2 | 1 day | T046
T128 | S11 | M7 | Testing | Frontend test — useXP() returns correct XP values and updates correctly after task completion | M | Dev 2 | 1 day | T073
T129 | S11 | M7 | Testing | Frontend test — FilterBar applies correct logic for All / Completed / High Priority / difficulty combos | M | Dev 2 | 1 day | T047
T130 | S11 | M7 | Testing | E2E Journey 1 — sign up, join workspace, connect Jira, sync tasks, complete task, verify XP on Dashboard | L | Shared | 2.5 days | T125
T131 | S11 | M7 | Testing | E2E Journey 2 — earn XP, purchase reward, verify coupon appears in My Rewards with correct expiry | L | Shared | 2.5 days | T130
T132 | S12 | M8 | Testing | E2E Journey 3 — purchase reward, confirm expiry warning shown, delete coupon, verify removal from My Rewards | M | Shared | 1 day | T131
T133 | S12 | M8 | Testing | E2E Journey 4 — Admin creates sprint, closes sprint, verify all developer XP bars reset to 0 | M | Shared | 1 day | T132
T134 | S12 | M8 | Testing | E2E Journey 5 — add Jira assignee → sync → TaskAssignment appears; remove → sync → TaskAssignment removed | L | Shared | 2.5 days | T133
T135 | S12 | M8 | Testing | Security tests — cross-workspace 403, Admin-only 403, wrong-workspace task completion 403 | M | Dev 1 | 1 day | T134
T136 | S12 | M8 | Testing | Security tests — unauthenticated 401, Developer closes sprint 403, tampered JWT 401, SQL injection safe | M | Dev 1 | 1 day | T135
T137 | S12 | M8 | Testing | Edge case tests (all 7): insufficient XP, expired coupons, double completion, no TaskAssignment, duplicate sprint, expired coupon, completed assignment preservation | L | Shared | 2.5 days | T136
T138 | S12 | M8 | Testing | Performance test — Jira sync with 100+ tasks and 10+ assignees/task completes within 3 seconds | M | Dev 1 | 1 day | T137
T139 | S13 | M8 | Testing | 10 developers complete different tasks simultaneously — no XP errors, no lost transactions (ACID guarantee) | M | Dev 1 | 1 day | T138
T140 | S13 | M8 | Testing | 5 developers purchase last coupon simultaneously — exactly one succeeds, others receive 400 | M | Dev 1 | 1 day | T139
T141 | S13 | M8 | Testing | Full coverage report — achieve ≥80% overall and 100% branch on critical modules; CI/CD gate passes | L | Shared | 2.5 days | T140
T142 | S13 | M8 | Documentation | Update ER diagram (questly-schema.mermaid) to reflect final schema with task_assignments table | M | Dev 1 | 1 day | T141
T143 | S13 | M8 | Documentation | Write API documentation — all endpoints: method, path, access level, request/response schema, error codes | M | Shared | 1 day | T142
T144 | S13 | M8 | Documentation | Write final project write-up — architecture, design decisions, testing strategy, lessons learned | L | Shared | 2.5 days | T143
T145 | S13 | M8 | Documentation | Prepare demo walkthrough for all 5 E2E journeys with talking points | M | Shared | 1 day | T144
T146 | S13 | M8 | DevOps | Final CI/CD run — all GitHub Actions checks green; upload final coverage report artifact | S | Shared | 0.5 day | T145
T147 | S13 | M8 | Documentation | Project submission — package all deliverables (repo, write-up, ER diagram, API docs, demo recording) | S | Shared | 0.5 day | T146
LAYER LEGEND | Backend | Frontend | Testing | DevOps | Design | Documentation

## Testing Checkpoints
Questly — Testing Checkpoints
All test gates by milestone ¦ Every milestone must pass its listed tests before closing
Milestone | Test Type | What Is Being Tested | Tool | Must Pass Before
M2 | DevOps | CI/CD pipeline runs and all jobs pass on first push to main (backend + frontend green) | GitHub Actions | Before M2 closes
M2 | Backend | All 10 DB migrations apply cleanly on a fresh PostgreSQL database with no errors | Knex migrations | Before M2 closes
M3 | Unit | generateToken(userId, role) returns valid JWT with correct payload | Jest | Before M3 closes
M3 | Unit | verifyToken(token) decodes valid token correctly; throws for expired or tampered token | Jest | Before M3 closes
M3 | Integration | POST /auth/register creates user + returns JWT; POST /auth/login correct → JWT; wrong password → 401 | Jest + Supertest | Before M3 closes
M3 | Integration | GET /auth/me returns user for valid token; returns 401 for missing or expired token | Jest + Supertest | Before M3 closes
M3 | Integration | Full join-request flow: Developer submits → Admin sees pending → Admin approves → Developer has workspace access | Jest + Supertest | Before M3 closes
M3 | Security | Developer calling Admin-only endpoint → 403 | Jest + Supertest | Before M3 closes
M3 | Security | Unauthenticated request to any protected endpoint → 401 | Jest + Supertest | Before M3 closes
M4 | Unit | mapJiraIssueToDifficulty(fields) maps all valid Jira field values to Easy/Medium/Hard; throws on unknown | Jest | Before M4 closes
M4 | Unit | diffTaskAssignments(jiraAssignees, dbAssignees) returns correct add/remove sets for all scenarios | Jest | Before M4 closes
M4 | Integration | Mocked Jira sync: new tasks upserted; existing tasks updated; no duplicate tasks (upsert idempotent) | Jest + Supertest + Nock | Before M4 closes
M4 | Integration | Mocked Jira sync: new Jira assignees get TaskAssignment rows; removed assignees lose rows only if completedAt IS NULL | Jest + Supertest + Nock | Before M4 closes
M4 | Integration | Sync run twice with same Jira data → no duplicate tasks or TaskAssignments | Jest + Supertest + Nock | Before M4 closes
M5 | Unit | calculateXP(difficulty) returns 20/40/70 for Easy/Medium/Hard; throws TypeError on unknown value | Jest | Before M5 closes
M5 | Integration | POST /tasks/:id/complete → XP added to current_sprint_xp and lifetime_xp; xp_transactions written; TaskAssignment.completedAt set | Jest + Supertest | Before M5 closes
M5 | Integration | Second POST /tasks/:id/complete on same TaskAssignment → 409; no duplicate XP awarded | Jest + Supertest | Before M5 closes
M5 | Integration | POST /tasks/:id/complete with no TaskAssignment for that task → 403 | Jest + Supertest | Before M5 closes
M5 | Integration | POST /sprints/:id/close → all workspace members' sprint XP reset to 0; sprint_reset xp_transaction written per user | Jest + Supertest | Before M5 closes
M5 | Integration | POST /workspaces/:id/sprints when one sprint is active → 409 ('A sprint is already active') | Jest + Supertest | Before M5 closes
M6 | Unit | isExpired(expiresAt) returns true when date is in past; false when future; handles null safely | Jest | Before M6 closes
M6 | Integration | POST /rewards/:id/purchase → XP deducted, coupon is_redeemed=true, Purchase created, coupon in My Rewards | Jest + Supertest | Before M6 closes
M6 | Integration | Purchase with insufficient current_sprint_xp → 400 | Jest + Supertest | Before M6 closes
M6 | Integration | Purchase when all coupons expired → 400; reward.is_available set to false | Jest + Supertest | Before M6 closes
M6 | Integration | DELETE /users/me/purchases/:id → deletedAt set; row in DB; not returned by subsequent GET | Jest + Supertest | Before M6 closes
M6 | Frontend | RewardShop: blocks buy button when XP insufficient; shows expired badge when expiresAt is past | Vitest + RTL | Before M6 closes
M6 | Frontend | MyRewards: renders coupon list correctly; delete triggers callback; expired coupons show warning | Vitest + RTL | Before M6 closes
M7 | Frontend | XPProgressBar renders correct fill width for given XP values; shows correct level label | Vitest + RTL | Before M7 closes
M7 | Frontend | TaskCard renders EASY/MEDIUM/HARD badge correctly; checkbox interaction triggers completion callback | Vitest + RTL | Before M7 closes
M7 | Frontend | useXP() hook returns correct currentSprintXP + lifetimeXP; updates correctly after task completion | Vitest + RTL | Before M7 closes
M7 | Frontend | FilterBar applies correct filter logic for All / Completed / High Priority / difficulty combinations | Vitest + RTL | Before M7 closes
M7 | E2E | Journey 1: Developer onboarding → join workspace → connect Jira → sync → complete task → XP on Dashboard | Playwright | Before M7 closes
M7 | E2E | Journey 2: Developer earns XP → purchases reward → coupon in My Rewards with correct expiry date | Playwright | Before M7 closes
M8 | E2E | Journey 3: Purchase reward → expiry warning shown → coupon deleted → removed from My Rewards view | Playwright | Before M8 closes
M8 | E2E | Journey 4: Admin creates sprint → active → closes sprint → all developer XP bars reset to 0 on Dashboard | Playwright | Before M8 closes
M8 | E2E | Journey 5: Add assignee in Jira → sync → TaskAssignment appears; remove assignee → sync → TaskAssignment removed | Playwright | Before M8 closes
M8 | Security | Developer calls Admin-only endpoint → 403; Developer from Workspace A accesses Workspace B tasks → 403 | Jest + Supertest | Before M8 closes
M8 | Security | Unauthenticated → 401; Developer closes sprint → 403; tampered JWT → 401; SQL injection in query params → safe | Jest + Supertest | Before M8 closes
M8 | Edge Case | Insufficient XP → 400; all coupons expired → 400; complete TaskAssignment twice → 409; no TaskAssignment → 403 | Jest + Supertest | Before M8 closes
M8 | Edge Case | Create sprint when one active → 409; redeem expired coupon → 400; sync preserves completed TaskAssignments | Jest + Supertest | Before M8 closes
M8 | Performance | Jira sync with 100+ tasks and 10+ assignees per task — completes within 3 seconds | k6 / Artillery | Before M8 closes
M8 | Performance | 10 concurrent task completions — no XP errors, no lost transactions (ACID guarantees hold) | k6 / Artillery | Before M8 closes
M8 | Performance | 5 concurrent reward purchases for last coupon — exactly one succeeds; others receive 400 | k6 / Artillery | Before M8 closes
M8 | Coverage | Full coverage ≥80% overall; XP logic, purchase flow, sprint close, Jira sync, TaskAssignment at 100% branch coverage; CI/CD gate passes | Jest + Vitest | Before M8 closes
TEST TYPE LEGEND | Unit | Integration | Security | E2E | Performance | Frontend | Coverage | Edge Case